## Slide 1: From Beta to Firm-wide: The Enterprise Rollout Plan
DATA RETENTION & DISPOSITION PLATFORM
A phased, feedback-driven path to adoption across the firm
Office of Data Governance · October 2026
Notes: Purpose: align leadership on how the DRD platform moves from a controlled beta to firm-wide adoption, and secure sponsorship for the go/no-go gate.

## Slide 2: Prove it with a few, then scale it to the firm
EXECUTIVE SUMMARY
We de-risk adoption by learning with a hand-picked beta cohort before every employee touches the platform
01
Start small
Select 10–15 domain stewards, custodians and data owners from BDS to train on and test the application
02
Enable deliberately
Run structured working sessions backed by explanation guides, quick-reference cards and recorded walkthroughs
03
Learn and improve
Capture feedback in every session, triage weekly and ship app updates in short release cycles
04
Scale on evidence
Gate firm-wide rollout on agreed exit criteria, then deploy in waves with hypercare support
Decision sought: endorse the beta cohort, the go/no-go criteria, and the wave-based firm-wide rollout

## Slide 3: Six phases from readiness to business-as-usual
ROLLOUT JOURNEY
0
Oct
Readiness
Freeze beta scope, stand up sandbox, finalize guides and feedback channel
1
Nov
Beta onboarding
Select BDS stewards, custodians and owners; kickoff and hands-on training session
2
Nov – Dec
Working sessions & feedback
Second session with owners and stewards; structured feedback collection on real use cases
3
Dec – Jan
Iterate & harden
Prioritize feedback, ship app updates, refresh guides, re-test with beta users
4
Jan
Go / No-Go
Assess against exit criteria; executive sign-off; finalize comms and support model
5
Feb – Mar
Firm-wide rollout & hypercare
Deploy in waves by division, champions network, then transition to BAU
Notes: Dates are indicative and assume a November beta start. Adjust once the beta cohort is confirmed.

## Slide 4: A small, representative cohort shapes the product
PHASE 1 · BETA COHORT
10–15
beta testers drawn from BDS
Mix of roles
Mix of data domains
Structured and shared-drive data
Committed for ~8 weeks
Data Owners
Approve retention outcomes and disposal sign-off; validate the decision workflow
Domain Stewards
Apply retention schedules to domain data; test classification and review screens
Data Custodians
Validate technical execution, inventory accuracy and disposition evidence
Selection criteria
Active retention responsibility, willingness to give candid feedback, and a real use case to test

## Slide 5: Two working sessions plus a self-serve kit
PHASE 2 · WORKING SESSIONS & ENABLEMENT
1
SESSION 1
Kickoff & hands-on training
Why DRD matters, platform walkthrough, guided tasks on beta users’ own domains, how to log feedback
2
SESSION 2
Feedback working session
Data owners and stewards share findings; walk through pain points live; agree priorities for the next release
Enablement kit
Explanation guide
What the platform does and why each step matters
Role quick-reference cards
One page per role: owner, steward, custodian
Recorded walkthroughs
Short videos for the core workflows
Sandbox environment
Safe data to practise on without risk
Office hours & feedback channel
Weekly drop-in plus a single place to log issues

## Slide 6: Every piece of feedback is captured, decided and closed
PHASE 3 · ITERATE & HARDEN
A weekly rhythm turns beta findings into app updates and sharper guides
Capture
Session notes, feedback form, office hours
Triage
Weekly: tag as defect, usability, enhancement or training gap
Prioritize
Severity × reach; must-fix before go-live vs backlog
Release
Short release cycles; update guides with each release
Close the loop
Tell beta users what changed and re-test with them
Rule of thumb: no open Severity 1–2 items and every piece of feedback dispositioned before go/no-go

## Slide 7: We scale only when the evidence says we are ready
PHASE 4 · GO / NO-GO GATE
Proposed exit criteria for executive sign-off (targets to confirm with sponsors)
≥ 90%
Task completion
Beta users complete core workflows unaided
0
Open Sev 1–2 defects
No critical or high defects outstanding
≥ 4 / 5
User satisfaction
Average beta rating of ease and usefulness
100%
Feedback dispositioned
Every item fixed, scheduled or explained
ALSO REQUIRED
Guides and training refreshed for final release
Support model and escalation path staffed
Division champions named for every wave
Data Owner disposal sign-off process confirmed

## Slide 8: Roll out in waves, each one easier than the last
PHASE 5 · FIRM-WIDE ROLLOUT
FEB
Wave 1
Beta domains go live
BDS and beta users move to production, acting as champions
FEB – MAR
Wave 2
Early adopter divisions
Divisions with mature stewardship and clear retention owners
MAR
Wave 3
Remaining divisions
All other data owners and stewards across the firm
MAR – APR
Hypercare
Stabilize & hand off
4–6 weeks of elevated support, then transition to BAU
Each wave repeats the beta playbook at scale: targeted comms, live training, guides, office hours, and a feedback channel that stays open

## Slide 9: Clear ownership at every step of the rollout
GOVERNANCE & OWNERSHIP
DRD Program (ODG)
Owns the plan, beta cohort, criteria, comms and go/no-go recommendation
Product & Engineering
Builds and releases app updates, runs defect triage, owns environments
Data Owners & Stewards
Test, give feedback, champion adoption in their divisions
Records & Information Mgmt
Partners on schedules and shared-drive disposition alignment
Legal & Compliance
Advises on defensible disposition and evidence requirements
Change & Communications
Firm-wide announcements, training calendar, intranet content

## Slide 10: Known risks, owned and mitigated up front
RISKS & MITIGATIONS
Risk | Impact | Mitigation
Beta users lack time to test | Thin or late feedback | Manager sponsorship, fixed session slots, small focused tasks
Feedback exceeds release capacity | Go-live slips | Severity-based triage; strict must-fix vs backlog line
Low adoption after go-live | Retention not applied consistently | Champions per division, role-based training, usage reporting
Disposition errors erode trust | Owner reluctance to sign off | Sandbox practice, review step before execution, audit evidence
Dependency delays (scanning, integration) | Wave timing at risk | Track dependencies weekly; waves can shift independently

## Slide 11
NEXT 30 DAYS
What happens next
1
Confirm beta cohort
Name 10–15 BDS stewards, custodians and owners; secure manager sponsorship
2
Finalize enablement kit
Explanation guide, role cards, walkthrough videos, sandbox ready
3
Schedule both sessions
Kickoff/training and the feedback working session on calendars
4
Agree exit criteria
Sponsors confirm go/no-go targets and sign-off forum
Ask of leadership: endorse the plan and sponsor the go/no-go gate in January