## Slide 1
PI 26.4 | Data Retention & Disposition
COMMITTED OBJECTIVES
PI Objectives
Operationalize policy-driven data retention and defensible deletion across the enterprise
Embed scalable retention governance into enterprise processes
Run the Business (RTB): RIM Program Acknowledgement; Data Retention Attestation roll-out
Feature Commitments
Start — Network / Shared Drive data retention work
Start — HCM UAT testing
Continue — Business Activity & Domain Retention Guidance
Continue — BigID configurations and validation
UNCOMMITTED OBJECTIVES (STRETCH)
Expand de-identification framework adoption for over-retained, analytically valuable data | Extend retention guidance to additional business domains beyond committed scope
DEPENDENCIES
DGS
BigID implementation — automation platform for retention rules
Data Stewards
Data assets research supporting retention mapping
Enterprise Architecture
Alignment to future-state platform strategies
Data Owners
Sign-off on data disposal (defensible deletion)
RISKS — WHAT COULD PREVENT OUR OBJECTIVES FROM BEING DELIVERED
BigID delivery timing delays retention automation | Data Owner sign-off latency blocks disposal execution | Steward capacity constrains asset research | HCM UAT environment availability impacts testing start
Notes: PI 26.4 one-pager: committed objectives (policy-driven retention + defensible deletion; scalable governance), feature commitments (Start: shared drives, HCM UAT; Continue: retention guidance, BigID config/validation), RTB items, dependencies (DGS/BigID, Stewards, EA, Data Owners), and derived risks.

## Slide 2
Talking Points | Walking Leaders & Partners Through PI 26.4
HOW TO FRAME IT
“This PI, DRD moves from defining retention policy to operationalizing it — automated retention rules with defensible deletion, embedded in enterprise processes rather than run as a side program.”
New this PI: shared-drive retention work and HCM UAT testing both start.
Continuing: domain retention guidance and BigID configuration/validation carry momentum from last PI.
Steady state: RIM acknowledgement and retention attestation roll-out keep compliance visible.
KEY HIGHLIGHTS TO LAND
Lower storage cost, lower regulatory risk: systematic disposal reduces what we pay to keep and what we're exposed to in audit or discovery.
Prevention over remediation: governing retention up front avoids expensive downstream cleanup and keeps us aligned to future-state architecture.
Audit readiness: attestation + defensible deletion give us evidence, not just policy.
Outcome: data systematically governed by automated retention rules; requirements consistently integrated.
WHAT WE NEED FROM PARTNERS
DGS: hold the BigID implementation timeline — it's the platform our automation commitments sit on.
Data Stewards: protect capacity for data-asset research; it feeds retention mapping directly.
Data Owners: timely disposal sign-off — every delayed approval delays defensible deletion.
Enterprise Architecture: early review so retention design lands inside future-state strategy, not beside it.
WHAT LEADERS SHOULD WALK AWAY WITH
1. DRD is shifting from policy to execution — retention and deletion become automated, evidenced, and enterprise-embedded this PI.
2. Our commitments are conditional on four named dependencies — the risks on the one-pager are the mirror image of those dependencies, and we're managing them openly.
3. The payoff is measurable: lower storage spend, reduced regulatory exposure, and audit-ready evidence of disposal.
Close: “If the dependencies hold, PI 26.4 is the quarter data retention stops being a document and starts being how the enterprise operates.”
Notes: Delivery guidance: open with the policy-to-execution framing, walk the one-pager top to bottom (objectives, stretch, dependencies, risks), land the three walk-away messages, and end with the specific asks of DGS, Stewards, Data Owners, and EA.